## Sheet1
| Quarter | Q3 | [11 empty] | Q4 | [12 empty] | Q1 | [12 empty] | Q2
Week Ending | time axis 2021-01-08 to 2021-12-31
ATTRACTION | Review branding | bar: 2021-01-08 to 2021-01-22
Merchandise/printing | bar: 2021-02-19 to 2021-02-26
Website content review | bar: 2021-01-29 to 2021-02-12
Career Fair Planning | bar: 2021-02-05 to 2021-02-19
Career Fair Attendance | bar: 2021-03-12 to 2021-03-26
RECRUITMENT | Stakeholder engagement
Number of hires confirmed
Recruitment strategy finalised
Job adverts finalised
Application form created
ATS setup complete
Hiring Managers confirmed
Shortlisting
Selection
Offers
Feedback
Contracts
Keep warm activities
Campaign review
ONBOARDING | Onboarding forms (HR forms)
Communication plan
Travel arrangements
Orientation program finalised
Venue bookings
Speakers booked
Materials
Invitations
Catering
Name badges
Participant feedback
DEVELOPMENT | Learning program finalised
Speakers booked
Venue bookings
Materials
Invitations
Catering
Name badges
Participant feedback
ROTATIONS | Stakeholder engagement
Participant engagement
Communication templates
Preferences collated
Preferences confirmed
Placements allocated
Stakeholders informed
Systems updated
STRATEGY | Program roll-off planning
Supplier contract review
Supplier check-in
Budget submission
Budget confirmation
Performance Review planning
Performance Review conversations
Performance Review confirmations
Remuneration Review
Reporting
Graduate Survey/Feedback
Leader Survey/Feedback